## Sheet1
Defect ID | TC id | TS id | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Module/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
D1 | TC1 | TS01 | Cycle1 | Build_ST_01 | System Testing | Release I | 2021-09-07 | Soumya Shet |  |  | Registration_PasswordMail |  | Description:registration page is not sending a mail containing password Expected result: enter the email id enter the first name enter the last name click on register button regiatration successful and password sent to mail Actual result: enter the email id enter the first name enter the last name click on register button regiatration successful and but password was not sent to mail | QA |  | High | Coding Errors | Y | Defect | High | open | User type: Regiatration is done successful and but password was not sent to mail. due to this login is unsuccessful. sending of mail should be done.
D2 | TC2 | TS02 | Cycle1 | Build_ST_02 | System Testing | Release I | 2021-09-07 | Soumya Shet |  |  | Login_ForgotPassword |  | Description:mail is not sent with new password Expected result: click on Lost Your Password? Enter email Id Click on Reset Password Sends a mail with new password Actual result: click on Lost Your Password? Enter email Id Click on Reset Password mail not sent with new password | QA |  | High | Coding Errors | Y | Defect | High | open | Forgot password is not sending a mail with a new passowrd to login.
D3 | TC3 | TS03 | Cycle1 | Build_ST_03 | System Testing | Release I | 2021-09-07 | Taznaine |  |  | Page not secure |  | Description:Page not secure | QA |  | High | Design | Y | Defect | High | open | As page is not secured , it ,might be affected
D4 | TC4 | TS04 | Cycle1 | Build_ST_04 | System Testing | Release I | 2021-09-07 | Sushmitha S |  |  | Admin_Comment_Quickedit |  | Desc: Admin should not be given access Expected Result: Navigate to comments Click on quick edit Input comment given in test data Input name given in test data Input email given in test data Input url given in test data Click on Update Comment button Updated comment should be visible Actual Result: Navigate to comments Click on quick edit Input comment given in test data Input name given in test data Input email given in test data Input url given in test data Click on Update Comment button Message"Admin should not be able to edit user comment" | QA |  | low | Requirement | Y | Defect | High | Open | Admin is given access to edit user comment which should not be given
D5 | TC5 | TS05 | Cycle1 | Build_ST_05 | System Testing | Release I | 2021-09-07 | Swathi M |  |  | Dashboard_WooCommercestatus |  | Should display the net sales of the month, the orders on hold, the orders on processing and also the products which are low and out of stock. | QA |  | low | Design Errors | Y | Defect | low | open | Admin should be able to view net sales of the month
D6 | TC6 | TS06 | Cycle1 | Build_ST_06 | System Testing | Release I | 2021-09-07 | Varshitha N |  |  | User Admin_AddNew_Email |  | Description: Sending the new user an email about their account failed. Expected Result: Input Username Input Email Input First Name Input Last name InputWebsite Show Password Checkbox for sending notification via mail Select Role Add new user button Actual Result: Input Username Input Email Input First Name Input Last name InputWebsite Show Password Checkbox for sending notification via mail Select Role Add new user button New User added by admin but no mail sent to user about their account | QA |  | low | Coding Errors | Y | Defect | low | open | When the inputs are in format and checkbox is checked ,Mail about account creation should be sent to the user. No mail received by User.
D7 | TC7 | TS07 | Cycle1 | Build_ST_7 | System Testing | Release I | 2021-09-07 | Soumya Shet |  |  | Enquiry_details |  | Description:send button not working Expected Result: enter name enter email give a subject give your message click on send the enquiry is sent to builder Actual Result: enter name enter email give a subject give your message click on send the enquiry is not sent to builder | QA |  | medium | Coding Errors | Y | Defect | High | open | The user send enquiry to the builder with respect to the property.but the enquiry send button is not sending the details to the builder
D8 | TC8 | TS08 | Cycle1 | Build_ST_8 | System Testing | Release I | 2021-09-07 | Swagata Malik |  |  | Search_with_tags&features |  | Description:search by tags and features is not included Expected result: in search enter name of the property or tags or features select the required property property details is displayed Actual result: in search enter name of the property or tags or features select the required property property details is displayed,but search by tags and features is not included | QA |  | medium | Design Errors | Y | Defect | High | open | Search can be done only through property name and description , but not with respect to tags and features
D9 | TC9 | TS09 | Cycle1 | Build_ST_9 | System Testing | RElease I | 2021-09-07 | Swagata Malik |  |  | User_My Profile |  | Description-Wrong phone number format is getting accepted. Expected result- Focus should go to Last Name field Focus should go to Agent Title field Focus Shoul go to Phone field Focus should go to E-mail field Focus should go to About me field Focus should upload Avatar field Focus should go to save changes button "There should not be any digits and special characters present in phone number " message should display Actual Result- Focus should go to Last Name field Focus should go to Agent Title field Focus Shoul go to Phone field Focus should go to E-mail field Focus should go to About me field Focus should upload Avatar field Focus should go to save changes button "your profile has been updated" message is showing | QA |  | Medium | Coding Errors | Y | Defect | High | Open | Wrong phone number format is getting updated .
D10 | TC10 | TS10 | Cycle2 | Build_ST_10 | System Testing | Release I | 2021-09-07 | Supriya Barthwal |  |  | Contact form |  | Description: Contact form page not able to send message Expected Result: Empty name field Input email Input subject Input message Click send button Message sent successfully Actual Result: Empty name field Input email Input subject Input message Click send button Error trying to send message | QA |  | medium | Coding Errors | Y | Defect | medium | open | Input fields are in format, message to be sent onclick of button. Message sending failed.
D11 | TC11 | TS11 | Cycle2 | Build_ST_11 | System Testing | Release I | 2021-09-07 | Supriya Barthwal |  |  | Contact form (web link) |  | Description: Web link not redirecting to the respective page Expected Result: Web link should redirect to the respective page Actual Result: Web link is not redirecting to the respective page | QA |  | medium | Coding Errors | Y | Defect | medium | open | Clicking on link is not redirecting to respective page
D12 | TC12 | TS12 | Cycle2 | Build_ST_12 | System Testing | Release I | 2021-09-07 | Varshitha N |  |  | Home page |  | Description: unable to redirect to respective website Expected Result: clicking on the icon should take you to the respective website Actual Result: Icon is not redirecting too the desired website (Google+,RSS) | QA |  | low | Coding Errors | Y | Defect | low | open | Icon is not redirecting too the desired website (Google+,RSS).
D13 | TC13 | TS13 | Cycle2 | Build_ST_13 | System Testing | Release I | 2021-09-07 | Taznaine |  |  | In Registration -length of First_name and Last_name is not specified |  | Description:registration page -length of first_name and last_name not specified Expected result: enter the email id enter the first name enter the last name click on register button regiatration successful and password sent to mail Actual result: enter the email id enter the first name enter the last name click on register button regiatration successful and but password was not sent to mail | QA |  | High | Coding Errors | Y | Requirement | Low | open | User type in registration page: Range/length for the First_name and Last_name is not specified
D14 | TC14 | TS14 | Cycle2 | Build_ST_014 | System Testing | Release I | 2021-09-07 | Supriya Barthwal |  |  | Password Change _length |  | Description: Upper boundary for password field is not specified Expected Result: Input current password Input new password Input correct confirm password Click on save changes button Password changed successfully Actual Result: Input current password Input new password Input correct confirm password Click on save changes button Password changed successfully | QA |  | High | Coding Errors | Y | Requirement | Low | open | Upper boundary for new password field and mandatory fields are not specified
D15 | TC15 | TS15 | Cycle2 | Build_ST_015 | System Testing | Release I | 2021-09-07 | Supriya Barthwal |  |  | Contact Form_format_length |  | Description: Contact form page length and format of name and email is not specified Expected Result: Empty name field Input email Input subject Input message Click send button Message sent successfully Actual Result: Empty name field Input email Input subject Input message Click send button Error trying to send message | QA |  | High | Coding Errors | Y | Requirement | Low | open | User type in Contact page: Format and length of name and email is not specified.
D16 | TC16 | TS16 | Cycle 2 | Build_ST_016 | System Testing | Release I | 2021-09-07 | Varshitha N |  |  | Admin User_AllUsers |  | Description: No bulk action is performed. Expected result: Select Bulk Action Select category to change role Apply changes Actual result: Select Bulk Action Select category to change role Apply changes | QA |  | Low | Coding Errors | Y | Requirement | Low | open | On selecting bulk action from drop down some action should be noticed. No action noticed
D17 | TC17 | TS17 | Cycle 2 | Build_ST_018 | System Testing | Release I | 2021-09-07 | Sushmitha s |  |  | Dashboard_WooCommerce recent reviews |  | Product reviews to be shown | QA |  | Low | Design error | Y | Requirement | Low | Open | Recent user product reviews to be dispalyed
D18 | TC18 | TS18 | Cycle2 | Build_RT_04 | System Testing | Release I | 2021-09-07 | Srishti Ghosh |  |  | AllProperty_search_withcategory |  | Description:Search property can only be done using title,its not working using other categories Expected result: Search property using Region Property details with the given region should get displayed Actual result: Search property using Region No properties found | Test |  | low | Design Errors | Y | Defect | medium | open | While searching in all properties , the search can only be done using title but cannot be done using other categories :Author,date,type,region and posted.
D19 | TC19 | TS19 | Cycle2 | Build_ST_05 | System Testing | Release I | 2021-09-07 | Sreelakshmi Ram A |  |  | Properties_settings_AdPropertyBanner |  | Description:Banner images are not displayed on top Expected Result: Banner images should get displayed at the top of page Actual Result: Banner images are getting displayed at the bottom of the page | QA |  | medium | UI | Y | Defect | low | open | After adding property banner image, the banner images is getting displayed at the bottom of every item page whereas it should get displayed at the top of item pages
D20 | TC20 | TS20 | Cycle2 | Build_ST_06 | System Testing | Release I | 2021-09-07 | Swagata Malik |  |  | AllPost_search_withcategory |  | Description:Search posts can only be done using title,its not working using other categories Expected result: Search post using category Post details with the given category should get displayed Actual result: Search post using category No posts found | QA |  | low | Design Errors | Y | Defect | low | open | While searching in all posts , the search can only be done using title but cannot be done using other categories :Author,date.
D21 | TC21 | TS21 | Cycle2 | Build_ST_05 | System Testing | Release I | 2021-09-07 | Swathi M |  |  | Admin_Comment_Edit_Approved |  | Description:Admin should not be given access to edit comment Expected Result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select approved Click on Update button Go to approved section and check whether the comment is present Actual Result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select approved Click on Update button Go to approved section the comment should be moved to approved section but admin cannot edit user comment | QA |  | medium | Requirement | Y | Defect | low | open | Admin can move the comment to approved section but admin should not be given access to edit user comment
D22 | TC22 | TS22 | Cycle2 | Build_ST_06 | System Testing | Release I | 2021-09-07 | Swathi M |  |  | Admin_Comment_Edit_Pending |  | Description:Search posts can only be done using title,its not working using other categories Expected result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select pending Click on Update button Go to pending section and check whether the comment is present Actual result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select pending Click on Update button Go to pending section the comment should be moved to pending section but admin cannot edit user comment | QA |  | low | Requirement | Y | Defect | low | open | Admin can move the comment to pending section but admin should not be given access to edit user comment
D23 | TC23 | TS23 | Cycle2 | Build_ST_05 | System Testing | Release I | 2021-09-07 | Swathi M |  |  | Admin_Comment_Edit_Spam |  | Description:Admin should not be given access to edit comment Expected Result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select spam Click on Update button Go to spam section and check whether the comment is moved to spam section Actual Result: Navigate to comments Click on edit Input author name given in test data Input email given in test data Input url given in test data Input comment given in test data Select spam Click on Update button Go to spam section the comment should be moved to spam section but the admin cannot edit user comment | QA |  | medium | Requirement | Y | Defect | low | open | Admin can move the comment to spam section but admin should not be given access to edit user comment

## Sheet2
Closed | Deferred | Duplicate | Invalid
299 | 4 | 3 | 8